## 1. START HERE
Aadit Technologies — Step-by-Step SEO / AEO / GEO Plan
Work through the phases in order. Do not start Phase 3 before Phase 1 is finished.
WHY THE ORDER MATTERS
Aadit gets 18,344 impressions and about 70 clicks in 90 days. The demand is already arriving.
The site is losing it to broken titles, duplicate URLs and pages competing with each other.
Adding new pages first would make the competition worse. Fix, then improve, then build.
Phase | What you do in it
PHASE 1 Stop the bleeding | Fix title tags, remove duplicate slash URLs, collapse redirect chains. Developer work. Converts rankings you already have into clicks. Nothing new gets written.
PHASE 2 Make pages AI-readable | Add FAQPage schema wherever an FAQ already exists. Add answer-first opening sentences. This is the AEO layer.
PHASE 3 Stop pages fighting | Consolidate the SOC cluster — 4 blog posts and their duplicates chase the same query. Pick one page per intent, redirect the rest.
PHASE 4 Expand what exists | Grow the 9 glossary pages from ~390 words to 800-1,200. Strengthen the 6 service pages. 57 of your 89 keywords are served by pages that already exist.
PHASE 5 Build the gaps | Build 8 new pages, highest opportunity first. Only after Phases 1-4.
THE THREE NUMBERS TO WATCH
Metric | Today
Clicks from Google | ~70 per 90 days
Copilot avg. cited pages | 1 (of 82 pages)
Queries with pages competing | 113
Tabs 2 to 5: the task list, your keyword clusters by seed, a per-page checklist, and the new pages to build.

## 2. Task List
Do these in order. Tick each one off.
Set Status to Done as you go. Column H shows how many are left.
# | Phase | Task | Exactly what to do | Where | Status
1 | P1 | Fix the title tag template | Titles are being cut mid-phrase with a stray ellipsis. "vapt full form" ranks position 1 with 741 impressions and ZERO clicks because the title reads "VAPT Full Form & Comprehensive VAPT... ¦ Aadit Technologies". Remove the hard character cut from the title builder. | Next.js metadata / buildTitle() | Not started
2 | P1 | Fix the meta description template | Same truncation bug. Descriptions end in "…" mid-sentence. Rewrite so descriptions are written to length, not cut to length. | Next.js metadata / buildDescription() | Not started
3 | P1 | Kill the 15 duplicate slash URLs | 15 pages are indexed at both /path and /path/. Google splits the signal. 1,954 impressions sit on the wrong version. Pick no-trailing-slash (matches your sitemap), 301 the slash form, make canonical tags agree. | Next.js config + canonical tags | Not started
4 | P1 | Collapse the double redirects | Legacy URLs go through two 308 hops before landing. Example: /blog/services-vapt-understanding-vapt/ to /blog/services-vapt-understanding-vapt to the real page. Map each legacy URL straight to its final destination. | redirects config | Not started
5 | P1 | Get the full pre-migration URL list | You have 4 confirmed legacy URLs still earning traffic and citations. There are more. Ask the developer for every URL that existed before the migration so one complete redirect map can be built. | Ask developer | Not started
6 | P2 | Add FAQPage schema to the VAPT page | That page has an H2 "Frequently Asked Questions (FAQ) about VAPT" and zero FAQPage markup. It carries 1.1K of your 1.3K Copilot citations. Mark up the existing Q&As. | /blog/vapt-full-form-comprehensive... | Not started
7 | P2 | Add FAQPage schema everywhere else | Any page with an FAQ section gets FAQPage, Question and acceptedAnswer markup. This is the single highest-value AEO change available. | All pages with FAQ sections | Not started
8 | P2 | Add answer-first opening sentences | Every service and glossary page opens with one sentence that directly answers the page title. AI engines quote that sentence. Put it above the fold, before any marketing copy. | 15 service + glossary pages | Not started
9 | P3 | Consolidate the SOC cluster | 4 blog posts plus slash duplicates chase the same query. "soc service providers in india" = 650 impressions across 5 URLs, best position 41. Keep /cybersecurity/managed-soc as the commercial page and ONE blog post as the informational page. 301 the other two into them. | 4 SOC blog posts | Not started
10 | P3 | Check the other cannibalisation cases | 113 queries have more than one Aadit page competing. Work down the Cannibalisation list from the previous workbook. Anything with 3+ URLs on one query needs consolidating. | Site-wide | Not started
11 | P4 | Expand /glossary/vapt | Currently 393 words. It has perfect DefinedTerm schema and earns zero citations while "vapt full form" pulls 938. Take it to 800-1,200 words: answer-first definition, how it works, when you need it, VA vs PT comparison table, FAQ block. | /glossary/vapt | Not started
12 | P4 | Expand the other 8 glossary pages | Same treatment for soc-2, iso-27001, siem, soc, gdpr, hipaa, pci-dss, vapt. These are definitional pages and definitional queries are what Aadit already wins. | /glossary/* | Not started
13 | P4 | Strengthen the 6 service pages | Service pages are almost invisible in Search Console — the blog carries everything. Add the mapped keywords, an FAQ block, and internal links from the matching blog posts with descriptive anchor text. | /cybersecurity/*, /compliance/*, /it-managed-services/* | Not started
14 | P4 | Link blog posts to service pages | Every blog post links to its matching service page using the service name as anchor text. This is how blog visibility transfers to the pages that sell. | 32 blog posts | Not started
15 | P5 | Build /resources/vapt-report-sample | Highest-opportunity gap: 1,140 searches at KD 12 and no page targets it. Buyers want to see the deliverable before they buy, so it doubles as a sales asset. | New page | Not started
16 | P5 | Build /compliance/iso-27001/india | Easiest wins on the whole list: "iso 27001 certification in bangalore" at KD 12, "in india" at KD 4. Commercial intent, $2+ CPC, and Aadit is in Bangalore. | New page | Not started
17 | P5 | Build /compliance/iso-27001/cost | 1,270 searches for ISO 27001 cost and nobody publishes ranges. A transparent cost page wins the query and pre-qualifies enquiries. | New page | Not started
18 | P5 | Build the remaining 5 new pages | vapt-career-guide, vapt/certificate, glossary/managed-it-services, soc-2-checklist, and the UAE page if Aadit actually serves UAE. See tab 5. | New pages | Not started
19 | -- | Re-measure | Re-check Bing AI Performance and Search Console 30 days after Phase 2 ships. Compare against the baseline: 1.3K citations / 1 avg cited page / 70 clicks. | Bing WMT + GSC | Not started
|  | Tasks remaining: | 19
|  | Tasks done: | 0
|  | Progress: | 0%

## 3. Clusters by Seed
Your 89 keywords, grouped by seed keyword
10 seed keywords. Each block is one cluster. Work one cluster at a time — that is how topical authority is built.
Keyword | Volume | KD | CPC | Intent | Target page | Action | Ranking now | Pos
SEED: iso 27001 certification | 9 keywords |  | 8,430 total vol |  | avg KD 31
iso 27001 certification | 5400 | 58 | 0.84 | Commercial | /compliance/iso-27001 | Expand existing | not ranking
iso 27001 certification cost | 880 | 27 | 0.65 | Commercial | /compliance/iso-27001/cost (new) | NEW PAGE | not ranking
iso 27001 certification in bangalore | 480 | 12 | 2.31 | Commercial | /compliance/iso-27001/india (new) | NEW PAGE | not ranking
iso 27001 certification cost in india | 390 | 16 | 0.87 | Commercial | /compliance/iso-27001/cost (new) | NEW PAGE | not ranking
iso iec 27001 certification | 390 | 54 | 1.03 | Commercial | /glossary/iso-27001 | Expand existing | not ranking
iso 27001 certification requirements | 260 | 32 | 0.71 | Commercial | /compliance/iso-27001 | Expand existing | not ranking
iso 27001 certification in india | 210 | 4 | 2.12 | Commercial | /compliance/iso-27001/india (new) | NEW PAGE | not ranking
iso 27001 certification service | 210 | 32 | 3.59 | Navigational | /compliance/iso-27001 | Expand existing | not ranking
what is iso 27001 certification | 210 | 41 | 0.25 | Commercial | /glossary/iso-27001 | Expand existing | /glossary/iso-27001 | 89
SEED: vapt | 23 keywords |  | 6,420 total vol |  | avg KD 20
vapt report | 720 | 12 | 2.6 | Commercial | /resources/vapt-report-sample (new) | NEW PAGE | not ranking
what is vapt | 720 | 18 | 0.39 | Commercial | /glossary/vapt | Expand existing | /blog/services-vapt-understanding-vapt/ | 30
vapt in cyber security | 590 | 19 | 0.76 | Commercial | /glossary/vapt | Expand existing | /blog/vapt-full-form-comprehensive-vapt-testing-services-in-india-aadit-technologies | 72
vapt tools | 590 | 23 | 2.13 | Commercial | /blog/best-vapt-tools-for-security-testing-aadit-technologies | Existing | /blog/best-vapt-tools-for-security-testing-aadit-technologies/ | 60
vapt certification | 480 | 29 | 0.63 | Commercial | /cybersecurity/vapt/certificate (new) | NEW PAGE | not ranking
vapt services | 480 | 27 | 2.35 | Navigational | /cybersecurity/vapt | Expand existing | /cybersecurity/vapt | 66
vapt audit | 260 | 15 | 2.56 | Commercial | /cybersecurity/vapt | Expand existing | not ranking
vapt course | 210 | 16 | 0.47 | Commercial | /resources/vapt-career-guide (new) | NEW PAGE | not ranking
vapt interview questions | 210 | 23 | 0 | Commercial | /resources/vapt-career-guide (new) | NEW PAGE | not ranking
vapt jobs for freshers | 210 | 21 | 0.03 | Navigational | /resources/vapt-career-guide (new) | NEW PAGE | not ranking
vapt report sample | 210 | 12 | 1.01 | Commercial | /resources/vapt-report-sample (new) | NEW PAGE | not ranking
vapt report template | 210 | 13 | 1.1 | Commercial/Navigational | /resources/vapt-report-sample (new) | NEW PAGE | not ranking
what is vapt in cyber security | 210 | 23 | 0.61 | Commercial | /glossary/vapt | Expand existing | /blog/services-vapt-understanding-vapt/ | 32
what is vapt testing | 210 | 18 | 0.3 | Commercial | /glossary/vapt | Expand existing | /blog/services-vapt-vapt-report | 77
vapt certificate | 170 | 19 | 0.59 | Commercial | /cybersecurity/vapt/certificate (new) | NEW PAGE | not ranking
vapt internship | 170 | 18 | 0.02 | Navigational | /resources/vapt-career-guide (new) | NEW PAGE | not ranking
vapt companies | 140 | 17 | 3.42 | Navigational | /cybersecurity/vapt | Expand existing | not ranking
vapt testing tools | 140 | 29 | 2.86 | Commercial | /blog/best-vapt-tools-for-security-testing-aadit-technologies | Existing | /blog/best-vapt-tools-for-security-testing-aadit-technologies/ | 74
network vapt | 110 | 18 | 0.63 | Commercial | /cybersecurity/vapt | Expand existing | not ranking
vapt analyst | 110 | 27 | 0.32 | Commercial | /resources/vapt-career-guide (new) | NEW PAGE | not ranking
vapt companies in india | 90 | 0 | 5.75 | - | /cybersecurity/vapt | Expand existing | not ranking
vapt jobs in hyderabad | 90 | 0 | 0.04 | - | /resources/vapt-career-guide (new) | NEW PAGE | not ranking
vapt testing services | 90 | 0 | 13.24 | - | /cybersecurity/vapt | Expand existing | /cybersecurity/vapt | 96
SEED: managed it services | 19 keywords |  | 4,720 total vol |  | avg KD 27
managed it services | 1900 | 35 | 2.06 | Commercial | /it-managed-services/managed-it-services | Expand existing | not ranking
managed it support services | 320 | 19 | 1.29 | Commercial | /it-managed-services/helpdesk-support | Expand existing | not ranking
managed services in it | 320 | 32 | 1.29 | Commercial | /it-managed-services/managed-it-services | Expand existing | not ranking
managed services it | 320 | 45 | 1.29 | Commercial | /it-managed-services/managed-it-services | Expand existing | not ranking
managed it services manchester | 170 | 18 | 0 | Navigational | — | Do not target | not ranking
what is managed it services | 170 | 32 | 0 | Commercial | /glossary/managed-it-services (new) | NEW PAGE | not ranking
it support and managed services | 140 | 30 | 0 | Commercial | /it-managed-services/helpdesk-support | Expand existing | not ranking
managed it services dubai | 140 | 17 | 1.06 | Navigational | /it-managed-services/managed-it-services/uae (new — only if Aadit serves UAE) | NEW PAGE | not ranking
managed it services houston | 140 | 41 | 2.68 | Navigational | — | Do not target | not ranking
it managed services companies | 110 | 36 | 4.37 | Commercial | /it-managed-services/managed-it-services | Expand existing | not ranking
it managed services new jersey | 110 | 22 | 10.02 | Navigational | — | Do not target | not ranking
managed it network services | 110 | 24 | 1.16 | Commercial | /it-managed-services/cloud-infrastructure | Expand existing | not ranking
managed it security services providers | 110 | 22 | 2.07 | Commercial/Navigational | /cybersecurity/managed-soc | Expand existing | not ranking
managed it services dallas | 110 | 30 | 4.06 | Navigational | — | Do not target | not ranking
managed it services dallas tx | 110 | 0 | 4.06 | Navigational | — | Do not target | not ranking
managed it services in dubai | 110 | 16 | 1.06 | Navigational | /it-managed-services/managed-it-services/uae (new — only if Aadit serves UAE) | NEW PAGE | not ranking
managed it services in los angeles | 110 | 18 | 4.78 | Navigational | — | Do not target | not ranking
managed it services los angeles ca | 110 | 23 | 4.78 | Navigational | — | Do not target | not ranking
managed it services nj | 110 | 19 | 10.02 | Navigational | — | Do not target | not ranking
SEED: cyber security services | 9 keywords |  | 3,550 total vol |  | avg KD 32
cyber security services | 1600 | 41 | 0.93 | Commercial | /cybersecurity | Expand existing | not ranking
cyber security audit services | 480 | 13 | 1.9 | Commercial | /compliance | Expand existing | not ranking
cyber security consulting services | 480 | 31 | 1.87 | Navigational | /cybersecurity/consulting | Expand existing | not ranking
cyber security services company | 320 | 38 | 1.41 | Navigational | /cybersecurity | Expand existing | not ranking
managed cyber security services | 210 | 34 | 2.01 | Commercial/Navigational | /cybersecurity/managed-soc | Expand existing | not ranking
cyber security services in india | 170 | 37 | 1.01 | Navigational | /cybersecurity (add India section) | Expand existing | not ranking
cyber security services near me | 110 | 29 | 0.53 | Transactional | /contact (needs Google Business Profile) | Expand existing | not ranking
cyber security testing services | 110 | 29 | 3.41 | Commercial | /cybersecurity/vapt | Expand existing | not ranking
cyber security management services | 70 | 0 | 2.22 | - | /cybersecurity | Expand existing | not ranking
SEED: soc 2 compliance | 6 keywords |  | 2,840 total vol |  | avg KD 47
soc 2 compliance | 1900 | 51 | 2.6 | Commercial | /compliance/soc2 | Expand existing | /blog/soc-2-compliance-services-india | 82
what is soc 2 compliance | 320 | 50 | 1.42 | Commercial | /glossary/soc-2 | Expand existing | not ranking
soc 2 compliance meaning | 260 | 51 | 2.11 | Commercial | /glossary/soc-2 | Expand existing | not ranking
soc 2 compliance checklist | 140 | 33 | 1.4 | Navigational | /resources/soc-2-checklist (new) | NEW PAGE | not ranking
soc 2 type 2 compliance | 110 | 50 | 3.58 | Commercial | /compliance/soc2 | Expand existing | not ranking
soc type 2 compliance | 110 | 49 | 3.58 | Commercial | /compliance/soc2 | Expand existing | /blog/soc-2-compliance-services-india | 71
SEED: cloud migration services | 4 keywords |  | 1,050 total vol |  | avg KD 28
cloud migration services | 720 | 36 | 1.25 | Commercial | /it-managed-services/cloud-migration | Expand existing | not ranking
aws cloud migration services | 110 | 31 | 1.3 | Commercial | /it-managed-services/cloud-migration (add AWS/Azure sections) | Expand existing | not ranking
azure cloud migration services | 110 | 21 | 2.14 | Commercial | /it-managed-services/cloud-migration (add AWS/Azure sections) | Expand existing | not ranking
cloud migration consulting services | 110 | 25 | 0 | Commercial | /it-managed-services/cloud-migration | Expand existing | not ranking
SEED: penetration testing services | 2 keywords |  | 760 total vol |  | avg KD 26
vulnerability assessment and penetration testing services | 590 | 28 | 23.25 | Commercial | /cybersecurity/vapt | Expand existing | not ranking
penetration testing services india | 170 | 23 | 5.25 | Commercial | /cybersecurity/vapt | Expand existing | not ranking
SEED: cyber security company | 4 keywords |  | 710 total vol |  | avg KD 21
cyber security company in kerala | 320 | 12 | 0.45 | Navigational | — | Do not target | not ranking
cyber security company in surat | 140 | 19 | 0.67 | Navigational | — | Do not target | not ranking
cyber security solutions company | 140 | 45 | 1.14 | Navigational | /cybersecurity | Expand existing | not ranking
cyber security company in kolkata | 110 | 9 | 0.44 | Navigational | — | Do not target | not ranking
SEED: soc as a service | 8 keywords |  | 490 total vol |  | avg KD 24
soc as a service | 210 | 30 | 1.61 | Commercial | /cybersecurity/soc-as-a-service | Expand existing | not ranking
soc as a service companies | 140 | 19 | 2.38 | Commercial | /cybersecurity/soc-as-a-service | Expand existing | /blog/top-soc-service-providers-in-india-secure-your-business/ | 84
soc as a service mssp | 30 | 0 | 0 | - | /cybersecurity/soc-as-a-service | Expand existing | not ranking
soc as a service providers | 30 | 0 | 2.81 | - | /cybersecurity/soc-as-a-service | Expand existing | /blog/top-soc-service-providers-in-india-secure-your-business/ | 76
soc as a service gartner | 20 | 0 | 0 | - | /cybersecurity/soc-as-a-service | Expand existing | not ranking
soc as a service meaning | 20 | 0 | 0 | - | /cybersecurity/soc-as-a-service | Expand existing | not ranking
soc as a service pricing | 20 | 0 | 1.63 | - | /cybersecurity/soc-as-a-service | Expand existing | not ranking
what is soc as a service | 20 | 0 | 0 | - | /cybersecurity/soc-as-a-service | Expand existing | not ranking
SEED: managed soc | 5 keywords |  | 260 total vol |  | avg KD 21
managed soc services | 140 | 21 | 2.56 | Commercial | /cybersecurity/managed-soc | Expand existing | /blog/managed-soc-services-managed-security-services-with-soc/ | 76
managed soc | 50 | 0 | 1.68 | - | /cybersecurity/managed-soc | Expand existing | /blog/managed-soc-services-managed-security-services-with-soc/ | 73
managed soc pricing | 30 | 0 | 0 | - | /cybersecurity/managed-soc | Expand existing | /cybersecurity/managed-soc | 45
managed soc providers | 20 | 0 | 3.14 | - | /cybersecurity/managed-soc | Expand existing | /blog/top-soc-service-providers-in-india-secure-your-business/ | 64
soc managed service providers | 20 | 0 | 0 | - | /cybersecurity/managed-soc | Expand existing | /blog/top-soc-service-providers-in-india-secure-your-business/ | 53

## 4. Page Checklist
What to do on each page
One row per page. These are the pages that already exist and need work.
Page | Keywords to target on it | Total vol | What to add | Status
/compliance/iso-27001 | iso 27001 certification (5,400) · iso 27001 certification requirements (260) · iso 27001 certification service (210) | 5870 | Answer-first opening · FAQ block with FAQPage schema · Service schema · internal links from matching blog posts | Not started
/it-managed-services/managed-it-services | managed it services (1,900) · managed services in it (320) · managed services it (320) · it managed services companies (110) | 2650 | Answer-first opening · FAQ block with FAQPage schema · Service schema · internal links from matching blog posts | Not started
/cybersecurity | cyber security services (1,600) · cyber security services company (320) · cyber security solutions company (140) · cyber security management services (70) | 2130 | Answer-first opening · FAQ block with FAQPage schema · Service schema · internal links from matching blog posts | Not started
/compliance/soc2 | soc 2 compliance (1,900) · soc 2 type 2 compliance (110) · soc type 2 compliance (110) | 2120 | Answer-first opening · FAQ block with FAQPage schema · Service schema · internal links from matching blog posts | Not started
/cybersecurity/vapt | vulnerability assessment and penetration testing services (590) · vapt services (480) · vapt audit (260) · penetration testing services india (170) · vapt companies (140) · cyber security testing services (110) · network vapt (110) · vapt companies in india (90) · vapt testing services (90) | 2040 | Answer-first opening · FAQ block with FAQPage schema · Service schema · internal links from matching blog posts | Not started
/glossary/vapt | what is vapt (720) · vapt in cyber security (590) · what is vapt in cyber security (210) · what is vapt testing (210) | 1730 | Answer-first definition in sentence 1 · expand to 800-1,200 words · comparison table vs the adjacent term · FAQ block with FAQPage schema | Not started
/it-managed-services/cloud-migration | cloud migration services (720) · cloud migration consulting services (110) | 830 | Answer-first opening · FAQ block with FAQPage schema · Service schema · internal links from matching blog posts | Not started
/blog/best-vapt-tools-for-security-testing-aadit-technologies | vapt tools (590) · vapt testing tools (140) | 730 | Fix title and description · add FAQ block with FAQPage schema · link to the matching service page | Not started
/glossary/iso-27001 | iso iec 27001 certification (390) · what is iso 27001 certification (210) | 600 | Answer-first definition in sentence 1 · expand to 800-1,200 words · comparison table vs the adjacent term · FAQ block with FAQPage schema | Not started
/cybersecurity/managed-soc | managed cyber security services (210) · managed soc services (140) · managed it security services providers (110) · managed soc (50) · managed soc pricing (30) · managed soc providers (20) · soc managed service providers (20) | 580 | Answer-first opening · FAQ block with FAQPage schema · Service schema · internal links from matching blog posts | Not started
/glossary/soc-2 | what is soc 2 compliance (320) · soc 2 compliance meaning (260) | 580 | Answer-first definition in sentence 1 · expand to 800-1,200 words · comparison table vs the adjacent term · FAQ block with FAQPage schema | Not started
/cybersecurity/soc-as-a-service | soc as a service (210) · soc as a service companies (140) · soc as a service mssp (30) · soc as a service providers (30) · soc as a service gartner (20) · soc as a service meaning (20) · soc as a service pricing (20) · what is soc as a service (20) | 490 | Answer-first opening · FAQ block with FAQPage schema · Service schema · internal links from matching blog posts | Not started
/compliance | cyber security audit services (480) | 480 | Answer-first opening · FAQ block with FAQPage schema · Service schema · internal links from matching blog posts | Not started
/cybersecurity/consulting | cyber security consulting services (480) | 480 | Answer-first opening · FAQ block with FAQPage schema · Service schema · internal links from matching blog posts | Not started
/it-managed-services/helpdesk-support | managed it support services (320) · it support and managed services (140) | 460 | Answer-first opening · FAQ block with FAQPage schema · Service schema · internal links from matching blog posts | Not started
/it-managed-services/cloud-migration (add AWS/Azure sections) | aws cloud migration services (110) · azure cloud migration services (110) | 220 | Answer-first opening · FAQ block with FAQPage schema · Service schema · internal links from matching blog posts | Not started
/cybersecurity (add India section) | cyber security services in india (170) | 170 | Answer-first opening · FAQ block with FAQPage schema · Service schema · internal links from matching blog posts | Not started
/contact (needs Google Business Profile) | cyber security services near me (110) | 110 | Needs a Google Business Profile before "near me" queries can work | Not started
/it-managed-services/cloud-infrastructure | managed it network services (110) | 110 | Answer-first opening · FAQ block with FAQPage schema · Service schema · internal links from matching blog posts | Not started

## 5. New Pages
8 new pages — build these last, in this order
Order | URL to create | H1 / page title | Keywords it serves | Vol | KD | Why | Status
1 | /resources/vapt-report-sample | What a VAPT Report Contains (With a Sample) | vapt report (720) · vapt report sample (210) · vapt report template (210) | 1140 | 12 | Biggest gap on the site. 1,140 searches at KD 12 and no page targets it. Also a sales asset — buyers want to see the deliverable before they buy. | Not started
2 | /compliance/iso-27001/india | ISO 27001 Certification in India and Bangalore | iso 27001 certification in bangalore (480) · iso 27001 certification in india (210) | 690 | 8 | Easiest keywords in the entire set — KD 12 and KD 4, commercial intent, $2+ CPC, and Aadit is physically in Bangalore. | Not started
3 | /compliance/iso-27001/cost | ISO 27001 Certification Cost in India | iso 27001 certification cost (880) · cost in india (390) | 1270 | 22 | Cost is the second question every buyer asks and nobody answers it publicly. Wins the query and pre-qualifies enquiries. | Not started
4 | /cybersecurity/vapt/certificate | VAPT Certificate: What You Get and What It Proves | vapt certification (480) · vapt certificate (170) | 650 | 24 | Splits "certify my company" from "certify me personally", then routes the commercial half to the VAPT service page. | Not started
5 | /resources/vapt-career-guide | VAPT as a Career: Roles, Skills and Interview Questions | vapt course (210) · vapt interview questions (210) · vapt jobs for freshers (210) · vapt internship (170) · vapt analyst (110) | 1000 | 19 | Not buyers — but 1,000 searches at low KD in the cluster Aadit already wins AI citations for. Builds authority, attracts links, feeds /careers. Keep it separate from commercial pages. | Not started
6 | /glossary/managed-it-services | What Are Managed IT Services? | what is managed it services (170) | 170 | 32 | The glossary covers security and compliance but has nothing for the managed IT line. Fills the gap and matches the definitional pattern Copilot cites. | Not started
7 | /resources/soc-2-checklist | SOC 2 Readiness Checklist | soc 2 compliance checklist (140) | 140 | 33 | The only SOC 2 keyword under KD 40 — the rest of that cluster averages 47 and is unwinnable at Authority Score 8. Also the most linkable asset in the compliance line. | Not started
8 | /it-managed-services/managed-it-services/uae | Managed IT Services in Dubai and the UAE | managed it services dubai (140) · in dubai (110) | 250 | 17 | CONDITIONAL — only if Aadit genuinely serves UAE clients. KD 16-17 makes it winnable. Do not build speculatively. | Not started

## 6. Do Not Target
11 keywords deliberately left out — and why
These have real search volume. They are still the wrong keywords for Aadit. Here is the reasoning so you can defend it to the client.
Keyword | Volume | KD | Why not
managed services it | 320 | 45 | US/UK generic with high difficulty and no geographic fit.
cyber security company in kerala | 320 | 12 | A searcher wanting a Kerala supplier. Aadit does not operate there. Low KD does not make it relevant.
managed it services manchester | 170 | 18 | UK city term. Needs a Manchester presence and local citations.
managed it services houston | 140 | 41 | US city term. Same reason.
cyber security company in surat | 140 | 19 | Surat supplier intent. Aadit does not operate there.
cyber security solutions company | 140 | 45 | High difficulty, vague intent, no differentiator.
cyber security company in kolkata | 110 | 9 | Kolkata supplier intent. KD 9 is tempting and still wrong.
it managed services new jersey | 110 | 22 | US city term.
managed it services nj | 110 | 19 | US city term.
managed it services dallas | 110 | 30 | US city term.
managed it services in los angeles | 110 | 18 | US city term.
The exception: Dubai. |  |  | "managed it services dubai" (140, KD 17) is on the New Pages tab marked CONDITIONAL, not skipped. It is the one international location term that fits a company positioning globally from India — but only build it if Aadit actually serves UAE clients.